## Sheet1
DEVELOPMENT TIMELINE
[6 empty] | January |  |  | February
TASK | ASSIGNED TO | STATUS | START | END | Estimated time (days) | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Development
Feature 1: Display Menu | Ikmal | completed | 2020-01-29 | 2020-01-30 | 2
Feature 2: Read and load maze from file | Ikmal | debugging | 2020-01-31 | 2020-02-04 | 5
Feature 3: View Maze | Qiao Ying
Feature 4: Play maze game | Shi Jie | completed | 2020-01-29 | 2020-02-04 | 7
Feature 5: Configure Maze | Jun Hong | completed | 2020-02-01 | 2020-02-04 | 4